## Task_Table1
Outline Number | Task Description | Status | Prime
1 | Define proposed extension
1.1 | Create Spreadsheet listing entities | Done | Elizabeh
1.2 | Map entities to existing C2SIM entities | In Progress | Elizabeth
1.3 | Create extension in OWL | In Progress | Michael
1.4 | Generate schema from OWL model
2 | Validate proposed extension
2.1 | Initialization Messages
2.1.1 | UC-01 Large urban area hit by Earthquake
2.1.2 | UC-02 Surveillance Swarm
2.1.3 | UC-05 Deploy resources via drone over a large area
2.1.4 | UC-07 Companion Drone (new)
2.2 | Order Messages
2.2.1 | UC-01-01 Earthquake aftermath: Deploy drones to search for survivors
2.2.2 | UC-01-02 Earthquake Aftermath: Request & Deliver Resources
2.2.3 | UC-02-01 Surveillance Swarm: Deploy Swarm
2.2.4 | UC-02-02 Surveillance Swarm: Swarm Leader goes silent
2.2.5 | UC-02-03 Surveillance Swarm: Change Flight Pattern
2.2.6 | UC-07-01 Companion Drone: Update drone flight path
2.3 | Report Messages
2.3.1 | UC-02-02 Surveillance Swarm: Swarm Leader goes silent
2.3.2 | UC-02-04 Surveillance Swarm: Report EW Intercept
2.3.3 | UC-03-01 Protect Troops: Recce Patrol Reports Swarm
3 | Review Proposed Schema
3.1 | Request review by SME(s)
3.2 | Request PDG group memebers review ASX proposal
3.3 | Update ASX based on feedback
4 | Propose extension to C2SIM PDG
4.1 | Prepare material for balloting
4.2 | Request Review
4.3 | Request Balloting